## Sheet1
Team | Sprint | What went well | Votes (Well) | What can be improved | Votes (Improve) | Action Items
Team 1 | 25.1.5 & 25.1.6 | Thank you team for taking up NY mandate changes on priority & completing everything (Analysis, mapping, model, Cod Changes & DDL Validation) | 1 | Team need to focus on preparing the documents in parallel with dev work | 2
|  | Thank you very much for all the efforts you made to send Proxy ID, CAG Benefit, Phase Indicator to UAT on time, as usual | 4 | Developers has to improve a bit in handing over stories to QA | 1
Team 1 | 25.1.5 & 25.1.6 | Thanks to Hari , for fixing issues related to input json in regression testing framework | 3 | it will be great if team can share the qtest links before the deadline | 2
|  | Thank you Anil & Asutosh for the benefit Consolidated table work UAT support and deployment and POST Prod support. | 2 | Logging the hours need to be continued with out any reminders. Please make it as a daily practice. | 3 | Team need to set reminder in outlook to log hours
|  | Sailaja & Nakshathra - Thank you for the efforts on Module Transition work. You delivered it Business on time without any issues | 3
Team 1 | 24.4.3 | Kudos Madhurya, for taking up the IRA CET and ensuring all the needful tasks are done accordingly. | 2
|  | Sailaja, great job working on the BCI Outbound CET via the DXU framework. Keep up the good work as usual. | 2
Team 1 | 24.3.3 | Thank you team for all the work on Weight Mgmt Program | 6
|  | CPSUI - Request and Response work is completed early than expected | 2
|  | Thank you Moksha for quickly adopting to the teams way of working | 2
Team 1 | 24.2.3 | Great work by team in solutioning Proxy ID | 1 | Test Scripts - Need to be peer reviewed | 6
|  | Team has shown good progress in Weight Mgmt - Most of the mapping, Model is done and dev is in good shape | 2 | Team size is not consistent each sprint, which makes some noise here and there | 0 | Please create Subtasks for Dev & QA Stories for code review & Test Scripts reviews
|  | Thanks to Narasimha for the support during Maha's Absence | 6
|  | Successfully completed Generic solution for ingesting Digital data into IDL | 3
|  | Good job done by developers in this sprint. Excellent support by Nakshathra | 3
|  | Thanks Madhurya for working on all projects and co-ordination during Maha absence. Good to see . | 4
Team 1 | 24.1.5 | Ensure RX - Delivered Successfully with out any issues in Go-Live . Thanks to the team | 3 | coming up with cost saving and optimizing solutions from existing or new domains | 1
|  | Team did a good job in completing EnsureRx CET & recon changes and deployed it into production. | 3 | LARK Project requirements are taking than expected. We would have been freeze requirements it early. | 4
|  | CAA - Planned deliverables deployed on time. Thanks Madhurya, Anil & QA Team. | 4
|  | Team is supporting CPDL Issues and involving in our team1 deliverables too. Good work. | 3
|  | Excellent support by Nakshathra and Asutosh. Learned a lot from both of them. Appreciate their help | 2
|  | Team making good progress on Digital dashboards SFTP setup | 3
Team 1 | 23.3.4 | Stories are handing over to QA team in frequently as compared to earlier | 2 | Having unit test cases developed in parallel with any new or enhancement to existing DAO | 1
|  | We are sending the completed work to Business for UAT approval on time. | 3 | Completing all pending LO handover so dev can take up more on code optimization and cost saving opportunities | 3
|  | As compare to before team has started uploading unit test cases in qtest on time . | 0 | full access for dev account, getting time consumed for small changes taking long time. [AP : | 5
|  |  |  | redshift full table access for SIT and DEV [to view data] | 0
Team 1 | 23.1.4 | Thanks to Maha for keeping track of everything and supportive always
Team 1 | 23.1.1 | PI 23.3 was planned with the requirements well, this time | 5 | We need to accommodate the work load balanced between team members (Including BSAs & Devs) | 1 | Everyone should have the Maven setup, and all the NLZ setups (hive, redshift) done. [AP: DEVs]
|  |  |  | Team need to adopt to the new requirements quickly and start developing as soon as we have some info is available, | 5
|  |  |  | Mapping & Modeling stories to be updated atleast few days in advance to start the dev work | 2
|  |  |  | Pending LO Handovers to be completed, if any and plan for hand over for new work as and when the work is completed | 3
Team 1 | 22.2.1 | kudo's to Sandeep for helping and explaining process flow. through out my first assignment. | 2 | Getting some changes to requirements in the last minute of Deployment dates(TPA Clients, Tertiary claims). So, getting delay in UAT Sign off | 1
|  | We have better PI Planning this time as we got requirements for new features during the meetings | 5 | Requirements are being changed in the middle of Testing , and going back and fourth with changes update makes very less time for end to end validation. The requirement change must be addressed and given final sign off before development starts please. | 2
|  | Though we have tight deadlines for Type8, IDL to Pharm feed, Manufacturer coupon view & IDURC 2022 changes, team has shown good commitment | 7 | Dev stories needs to be taken up once model document is ready to deliver task on time with more accuracy. | 5
|  | kudo's to sarath for sharing knowledge on hummer framework. | 2
|  | Kudos to Nakshathra and Anil for being actively on top of Cost Relief effort and delivering them swiftly! | 2
|  | Process is improved since Jagadish is here as he is talking to each other and taking care on work items | 3
|  | Collaboration between BSA, DA, Dev's and QA's is phenomenal. As a team, we are supporting each other, | 4
|  | Every week PROD deployments are going as per plan and without any issues. Thank you team!!! | 6
Team 1 | 22.4.5 |  |  | Early availability of test files for business review from source teams will yield early identification of unprecedented scenarios. | 6
Team 3 | 24.4.2 | Thank you Sri Lakshmi for working hard towards the Raven - Benefits deployment as per the plan, | 3
|  | Thanks to Venkata Singu for completing Raven - Eligibility changes and deployment support | 2
|  | Thank you Srikanth for following up & Support with JIT Team for getting CET Claims Apporval. | 5
|  | Venkata Sarath - Thank you for for actively working on RLS changes, all tables completion & deployments. | 7
|  | Pavani has been working hard, helpful and approachable at any time for any support. | 5
|  | Well done team, for the coordination, support and dedication to complete the priority items in the sprint | 2
|  | everything went well In this Sprint, Thank you Team for your support . | 4
|  | thank you Sri Lakshmi and Satish for your Input in Raven validation | 3
Team 3 | 24.4.3 | Thank you Srilakshmi & Mani for the CDP Deployment & Load Support over weekend | 2
|  | Bioplus Code changes are on track Thanks to team. | 3
|  | Thanks to Pavani for round the clock support. | 5 | Can dev team plan to handover QA validation by 6th or 7th day of the sprint, please. | 3
Team 3 | 24.3.1 | Thanks to Srikanth for taking up BNFT_NTWK Tables | 3 | Base Network - NTWK_DIR_PHRMCY_LIST Build time is taking longer than expected. Should have come early with the implediments | 3
|  | Thanks to Pavani for the co-ordination with the teams & business | 3 | Dev team need to hand over the stories to QA team by mid of sprint instead of 9th /10th day of sprint | 1
|  |  |  | Raven projects should be expediated w.r.t build completion | 0
Team 2 | 25.1.1 & 25.1.2 | CII Environment. Framework Setup is going well.. Thank you for the efforts . | 3 | Logging the hours need to be continued with out any reminders. Please make it as a daily practice. | 1
|  | Team is collaborating and helping each other to meet sprint goal. Good Job. | 3 | Please update Unit Test Cases to qTest before end of the sprint | 2
|  | Thanks to Mani for support on CII work | 2
Team 2 | 25.1.5 & 25.1.6 | CII Integration - Thank You team for all work & efforts for deploying Tables on 02/28 & 03/14 as per plan. We deployed 15 Tables | 5 | Getting CII data models on time, but other projects data models to be expediated and also get DG approval before handing over to team | 4
|  | Special Thanks to Suresh for taking up all additional responsibilities and tracking the dev work | 3 | Team is working over capacity, Kindly distribute the work as per bandwidth | 5
|  | Thank you Mani for all the deployment support activities and coordinating with AEDL & Snowflake teams | 1 | Developers has to improve a bit in handing over stories to QA | 2
|  | Thanks To Pavani for supporting the team and up-to-date info across all projects | 2
|  | Thanks to QA team for all the good work. | 1
Team 1 | 22.1.5 | Kudos to Dev and testing team for quick delivery of CRE tables implementation ( For Care gaps & Refill reminder) | 7 | Some of the requirements are been hold after doing analysis (Ex: Manufacturer coupon view ) and some are after dev (Ex: Primary claims, Refill reminder) because of design change. We need to keep improve in this area by freezing the requirements on sprint planning day) | 3
|  | Thank you Team for all your help and support. It was a great start with my new project and everyone delivers their work on time. | 3 | Requirements gathering, putting details in acceptance criteria in JIRA and put the correct story points. If requirements change create new US and do not carry on the work in the same US | 8
|  | Weekly PROD deployments are going smoothly with out any issues. | 3 | It will be possible to deliver in time if we can have finalized schema file and model before deciding on the deadlines of development stories | 2
|  | Thank you to Dev Lead, QA Lead, BAs and even SM who is helping the team all the times. | 5 | At least 40% of the stories need to be closed by mid of the sprint. | 4
Team 1 | 22.2.2 | Thanks to Dev and Testing team for being able to Deliver IDURC 2022 changes on-time. That required a great deal of co-ordination among team. | 7 | Please ask the business teams to have a well defined scope and their timelines, POC and same goes for the source teams! | 3 | Accurately identify source teams Technical SME POC in the beginning of Analysis phase to help with requirements/solution design. - BSA's/PO
|  | Appreciate Neetu and Manasa for being on top of TPA work to get it delivered in time and special thanks to Manasa | 6
|  | Appreciate Manoj efforts in RRR, CMR and GIT | 4
|  | Manufacturer coupon view code changes completed on time and deployed as per time lines. Thank you team !!! | 4
|  | Akash, Anil, Sandeep, Nakshathra. History claims load in PROD was a huge task, lot of extra hours, thank you for completing it smoothly. | 8
|  | Thanks to Balakrishna for the great work in EMR migration work and supporting the team over weekend | 3
|  | Appreciate Nakshathra, Ayushi and Manasa for their work on IDURC | 2
Team 1 | 23.4.4 | Work on Lambdas were very well coordinated | 2 | SC - Going in a slow pace than expected, Need quicker support Business | 4 | Quicker support from business on pending projects/items
|  | Team distributing the work well considering the leaves/holidays period | 2 | QA should be more involved in data analysis and root cause analysis of issues. All the observations/issues should be reported during testing phase. | 6
|  | Thanks team for working on some improvements (medical file optimizations, "file_nm" changes) | 0
|  | Major features code changes and validation has been done | 2
|  | Good support from the team. | 5
|  | Maha is been supporting the BSAs very well to speed up the things | 3
|  | Great planning during the holiday season and execution of the tasks from every team member. Kudo to the team for the great co-ordination | 8
Team 1 | 23.3.3 | Thank you Krishna, Nakshathra for taking up BCI-Medical Extracts work on middle of sprint and in a good position by last day of sprint. | 3 |  |  | Once dev and testing is completed everyone should upload test results in qTest without delay and ask
|  | Team is improved with handing over the dev stories to QA Team | 2
Team 1 | 23.3.2 | Thank you team for the efforts made in the sprint, we are going in a good shape | 3 | Need to handover the DEV-completed stories to QA team by mid of Sprint (improved recently) | 4
|  | Thank you Madhurya for taking up additional responsibilities in the sprint (Helping Mahes & ASO Mapping stories) and coordination with Maha | 7 | Active Participation in Retro Meetings :-) | 2
|  | Team has evolved quite well and thanks to all the members of team for their consistent deliverables in the sprints | 4 | once dev and testing is completed everyone should upload test results in qtest without delay or follow ups. | 5
|  | Thank you Krishna for IBC-Coordination work | 6
|  | Team made habit of updating the mapping docs in confluence and to stories. It definitely helpful in future | 0
Team 1 | 23.1.1 | Benefit Normalization - Deployed on time. Thanks to Both Dev & QA teams. | 5 | Dev team need to improve in handing over the changes to QA team bit early. | 3
|  | Good work krishna on the IBC work and Test cases for hummer framework. | 4 | Team Adhoc Leaves - to be reduced | 3
|  | Thanks to Jagadish for his work for creating the Change tickets, follow ups for deployments during last week of Dec | 8 | To avoid any kind of rework we need to make sure the mapping and modeling is finalized before taking up any feature. | 8
|  | Super Support from Nakshathra & Sandeep as usual. | 9 | Requirements still taking time/ changing in middle - BSA's please inform the business about timeline in advance. They MUST aware timelines. | 5
|  | Special Thanks to Manasa for her extended support during 01/01 implementation | 6
Team 1 | 22.1.4 | Like to thank Krishna, Nakshathra and Sandeep for there inputs in TPA Claims automation enhancement. | 2 | Requirement discussions are taking longer time as a result it might miss delivery timelines | 5 | Need to track dependency better so that impact on development work can be tracked efficiently [Action : PO/SA]
|  | Even though we are working in different time zones, communication and collaboration between the team members is good. | 5 | Need a better process to interact with other teams: despite of having a clear Agenda team did not answer the questions, which delayed | 3
|  | Communication and Team support in IDL team is good | 7
|  | Amazing work by Aditya, Neetu, Sandeep, Nakshathra and Akash on technical spike related to Medical Claims SUP_ORGNL_CLM_NBR | 4
|  | Like to thank Nakshathra and Akash for their support in setting up environments and giving kt's and helping to understand the process. | 3
|  | Proactive team participation in all Scrum Ceremonies. | 6
Team 2 | 25.1.3 & 25.1.4 | Team is working hard to meet the CII - UAT Delivery timelines | 3 | QA Understand the Dev efforts on CII Tables, but it would be good if the dev team can handover for validation bit early | 5
|  | Thank You the team for your dedication & efforts you are showing on CII Project | 4 | Model & Mapping for CII Tables MUST be in sync before the build/validation commence | 3
|  | Thank you Selvi for all the development completion & deployment for Rebate Derived project | 2